## Status Report 8-27
Status Report for Austin Wong - Spelling Bee Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-08-27 | Overall Status: | Green
Contact: | Austin | Explanation:
Prepared By: | Austin
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Austin | Finished preliminary API research
Austin | Drafted high-level project requirements and received project approval
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date (EOD) | Comment/Status
Environment setup |  | 0% | 2021-08-28
FRONT-END |  | 0% | 2021-09-01
Low fidelity wireframing |  | 0% | 2021-08-28
Html pages |  | 0% | 2021-09-01
BACK-END |  | 0% | 2021-08-31
Database design |  | 0% | 2021-08-29
Schema creation scripts |  | 0% | 2021-08-29
DAO |  | 0% | 2021-08-30
API Calls |  | 0% | 2021-08-31
Business logic |  | 0% | 2021-08-31
TESTING |  | 0% | 2021-09-01
Unit Testing |  | 0% | 2021-08-30
Functional Testing |  | 0% | 2021-09-01
Presentation (Practice) |  | 0% | 2021-09-01
Presentation (Actual) |  | 0% | 2021-09-02

## Status Report 8-30
Status Report for Austin Wong - Spelling Bee Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-08-30 | Overall Status: | Green
Contact: | Austin | Explanation:
Prepared By: | Austin
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Austin | Completed low-fidelity wireframing
Austin | Completed ERD
Austin | Created schema creation scripts
Austin | Created test-data creation scripts
Austin | Documented necessary endpoints and JSON format for 3rd party API calls
Austin | Set up environment
Austin | Created backbone of HTML pages
Austin | Created model classes in Netbeans
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date (EOD) | Comment/Status
Environment setup |  | 100% | 2021-08-28
FRONT-END |  | 50% | 2021-09-01
Low fidelity wireframing |  | 100% | 2021-08-28
Html pages |  | 50% | 2021-09-01
BACK-END |  | 25% | 2021-08-31
Database design |  | 100% | 2021-08-29
Schema creation scripts |  | 100% | 2021-08-29
DAO |  | 0% | 2021-08-30
API Calls |  | 20% | 2021-08-31
Business logic |  | 0% | 2021-08-31
TESTING |  | 0% | 2021-09-01
Unit Testing |  | 0% | 2021-08-30
Functional Testing |  | 0% | 2021-09-01
Presentation (Practice) |  | 0% | 2021-09-01
Presentation (Actual) |  | 0% | 2021-09-02

## Status Report 8-31
Status Report for Austin Wong - Spelling Bee Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-08-31 | Overall Status: | Green
Contact: | Austin | Explanation:
Prepared By: | Austin
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Austin | Completed writing unit tests
Austin | Completed writing DAO DB implementations
Austin | Service layer finished
Austin | All unit tests passed
Austin | Added questionNumber field in quizword table in DB to account for word order on each quiz
ID # | Key Issues | Action Plan |  |  | Status
1 | Difficulties parsing JSON response to get a couple fields (but they are indeed in the response) | Work through parsing a String of JSON response without making new API calls |  | In Progress
2 | Possible that "vis" field (holds example sentences) from JSON response is not populated for several entries | Investigate a larger set of data to see if this actually the case or just small sample size. May need to discuss removing example sentence feature |  | In Progress
Critical Milestones |  | Health | Due Date (EOD) | Comment/Status
Environment setup |  | 100% | 2021-08-28
FRONT-END |  | 65% | 2021-09-01
Low fidelity wireframing |  | 100% | 2021-08-28
Html pages |  | 50% | 2021-09-01
BACK-END |  | 85% | 2021-08-31
Database design |  | 100% | 2021-08-29
Schema creation scripts |  | 100% | 2021-08-29
DAO |  | 100% | 2021-08-30
API Calls |  | 40% | 2021-08-31
Business logic |  | 80% | 2021-08-31
TESTING |  | 60% | 2021-09-01
Unit Testing |  | 100% | 2021-08-30
Functional Testing |  | 20% | 2021-09-01
Presentation (Practice) |  | 0% | 2021-09-01
Presentation (Actual) |  | 0% | 2021-09-02

## Status Report 9-1
Status Report for Austin Wong - Spelling Bee Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-09-01 | Overall Status: | Green
Contact: | Austin | Explanation:
Prepared By: | Austin
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Austin | Refactored a lot of code to better follow MVC design
Austin | Revised Word model to better follow format of API call
Austin | Revised DAO and Service layer to accommodate above changes
Austin | Passed regression tests
Austin | Webpages are functional!
Austin | Resolved issues with JSON parsing
ID # | Key Issues | Action Plan |  |  | Status
1 | Difficulties parsing JSON response to get a couple fields (but they are indeed in the response) | Resolved |  | Resolved
2 | Possible that "vis" field (holds example sentences) from JSON response is not populated for several entries | Resolved |  | Resolved
Critical Milestones |  | Health | Due Date (EOD) | Comment/Status
Environment setup |  | 100% | 2021-08-28
FRONT-END |  | 85% | 2021-09-01
Low fidelity wireframing |  | 100% | 2021-08-28
Html pages |  | 70% | 2021-09-01
BACK-END |  | 100% | 2021-08-31
Database design |  | 100% | 2021-08-29
Schema creation scripts |  | 100% | 2021-08-29
DAO |  | 100% | 2021-08-30
API Calls |  | 100% | 2021-08-31
Business logic |  | 100% | 2021-08-31
TESTING |  | 85% | 2021-09-01
Unit Testing |  | 100% | 2021-08-30
Functional Testing |  | 70% | 2021-09-01
Presentation (Practice) |  | 0% | 2021-09-01
Presentation (Actual) |  | 0% | 2021-09-02

## Status Report 9-2
Status Report for Austin Wong - Spelling Bee Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-09-01 | Overall Status: | Green
Contact: | Austin | Explanation:
Prepared By: | Austin
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Austin | Completed powerpoint presentation
Austin | Practiced powerpoint presentation
Austin | Added text-to-speech for definition and example sentence
Austin | Hid definition and example sentence by default and added toggle buttons
Austin | Revised text-to-speech to ensure program vocalized hidden word in example
Austin | Ensured abandoned quizzes (quizzes with no guesses) were removed upon loading history
Austin | Tested program in Firefox and Chrome
ID # | Key Issues | Action Plan |  |  | Status
1 | Difficulties parsing JSON response to get a couple fields (but they are indeed in the response) | Resolved |  | Resolved
2 | Possible that "vis" field (holds example sentences) from JSON response is not populated for several entries | Resolved |  | Resolved
Critical Milestones |  | Health | Due Date (EOD) | Comment/Status
Environment setup |  | 100% | 2021-08-28
FRONT-END |  | 100% | 2021-09-01
Low fidelity wireframing |  | 100% | 2021-08-28
Html pages |  | 100% | 2021-09-01
BACK-END |  | 100% | 2021-08-31
Database design |  | 100% | 2021-08-29
Schema creation scripts |  | 100% | 2021-08-29
DAO |  | 100% | 2021-08-30
API Calls |  | 100% | 2021-08-31
Business logic |  | 100% | 2021-08-31
TESTING |  | 100% | 2021-09-01
Unit Testing |  | 100% | 2021-08-30
Functional Testing |  | 100% | 2021-09-01
Presentation (Practice) |  | 100% | 2021-09-01
Presentation (Actual) |  | 0% | 2021-09-02