## Status Report 8-27
Status Report for Austin Wong - Spelling Bee Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-08-27 | Overall Status: | Green
Contact: | Austin | Explanation:
Prepared By: | Austin
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Austin | Finished preliminary API research
Austin | Drafted high-level project requirements and received project approval
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date (EOD) | Comment/Status
Environment setup |  | 0% | 2021-08-28
FRONT-END |  | 0% | 2021-09-01
Low fidelity wireframing |  | 0% | 2021-08-28
Html pages |  | 0% | 2021-09-01
BACK-END |  | 0% | 2021-08-31
Database design |  | 0% | 2021-08-29
Schema creation scripts |  | 0% | 2021-08-29
DAO |  | 0% | 2021-08-30
API Calls |  | 0% | 2021-08-31
Business logic |  | 0% | 2021-08-31
TESTING |  | 0% | 2021-09-01
Unit Testing |  | 0% | 2021-08-30
Functional Testing |  | 0% | 2021-09-01
Presentation (Practice) |  | 0% | 2021-09-01
Presentation (Actual) |  | 0% | 2021-09-02

## Status Report 8-30
Status Report for Austin Wong - Spelling Bee Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-08-30 | Overall Status: | Green
Contact: | Austin | Explanation:
Prepared By: | Austin
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Austin | Completed low-fidelity wireframing
Austin | Completed ERD
Austin | Created schema creation scripts
Austin | Created test-data creation scripts
Austin | Documented necessary endpoints and JSON format for 3rd party API calls
Austin | Set up environment
Austin | Created backbone of HTML pages
Austin | Created model classes in Netbeans
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date (EOD) | Comment/Status
Environment setup |  | 100% | 2021-08-28
FRONT-END |  | 50% | 2021-09-01
Low fidelity wireframing |  | 100% | 2021-08-28
Html pages |  | 50% | 2021-09-01
BACK-END |  | 25% | 2021-08-31
Database design |  | 100% | 2021-08-29
Schema creation scripts |  | 100% | 2021-08-29
DAO |  | 0% | 2021-08-30
API Calls |  | 20% | 2021-08-31
Business logic |  | 0% | 2021-08-31
TESTING |  | 0% | 2021-09-01
Unit Testing |  | 0% | 2021-08-30
Functional Testing |  | 0% | 2021-09-01
Presentation (Practice) |  | 0% | 2021-09-01
Presentation (Actual) |  | 0% | 2021-09-02

## Status Report 8-31
Status Report for Austin Wong - Spelling Bee Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-09-01 | Overall Status: | Green
Contact: | Austin | Explanation:
Prepared By: | Austin
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Austin | Completed writing unit tests
Austin | Completed writing DAO DB implementations
Austin | All unit tests passed
Austin | Added questionNumber field in quizword table in DB to account for word order on each quiz
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date (EOD) | Comment/Status
Environment setup |  | 100% | 2021-08-28
FRONT-END |  | 65% | 2021-09-01
Low fidelity wireframing |  | 100% | 2021-08-28
Html pages |  | 50% | 2021-09-01
BACK-END |  | 72% | 2021-08-31
Database design |  | 100% | 2021-08-29
Schema creation scripts |  | 100% | 2021-08-29
DAO |  | 100% | 2021-08-30
API Calls |  | 20% | 2021-08-31
Business logic |  | 40% | 2021-08-31
TESTING |  | 50% | 2021-09-01
Unit Testing |  | 100% | 2021-08-30
Functional Testing |  | 0% | 2021-09-01
Presentation (Practice) |  | 0% | 2021-09-01
Presentation (Actual) |  | 0% | 2021-09-02